## CRM
[6 empty] | ICC: | John A. Kasper | [17 empty] | CRM_TEMPLATE.XLXM, v 2009-11-09
[6 empty] | ICC Phone Number: | 310-414-2838
[6 empty] | Baselined Document (CCB Version): | IS-GPS-240A & IS-GPS-870B
[6 empty] | Proposed Change: | Update IS-GPS-240A and IS-GPS-870B, Section 10.2 NANU Notification Times, in order to provide clarification of the requirement and to mitigate any potential delays of the PPS PS and SPS PS for NANU issuanace (as proposed by Aerospace).
[6 empty] | Title: | RFC-352, Update ICD-GPS-240 and ICD-GPS-870 for NANU Issuance
[6 empty] | Date: | 2017-03-13
[6 empty] | Tech Lead Name: | John A. Kasper, 310-414-2838
For instructions see the "INSTRUCTIONS" TAB below
Commenter Identification Fields |  |  |  | Comment Description Fields | [6 empty] | ICC Disposition Fields | [8 empty] | Commenter Concurrence Fields |  | ICC Concurrence Fields
| Gov | GPSW/CC |  |  |  | C - Critical |  |  |  |  | Pre-WG |  | Baselined Doc |  | Y | Addition | Accept with Comments |  |  | Concur |  | email |  | Open
| SE&I | GPSW/CV |  |  |  | S - Substantive |  |  |  |  | WG |  | Proposed Change |  | N | Change | Accept |  |  | Non Concur |  | phone |  | Closed
| FFRDC | GPSW/GPA |  |  |  | A - Administrative |  |  |  |  | WTR |  |  |  |  | Deletion | Defer |  |  |  |  | meeting
|  | GPSW/GPC | [8 empty] | Post-WTR | [5 empty] | Reject
|  | GPSW/GPD |  |  |  | J. Bolger
GPSW/EN
GPSW/GPCG
GPSW/GPSG
GPSW/PC
GPSW/PK
GPSW/OS
GPSW/GPN
GPSW/GPUG
GPSW/GPV
GPSW/GPW
SE&I
Aerospace
AFSPC/50 SW
AFSPC/A5P
SETA
FFRDC
SE&I
Prime Ctr
Other
(1) COMMENT NO. | (2) ENTITY | (3) OFFICE SYMBOL | (4) COMMENTER NAME | (7) DOC LINE# (if applicable) | (8) PARA # | (9) COMMENT TYPE (C/S/A) | (10) COMMENT | (11) ORIGINAL TEXT ( FROM ) | (12) SUGGESTED CHANGE ( TO ) | (13) RATIONALE FOR CHANGE | (14) DOC PHASE | (15) DATE of COMMENT (mm/dd/yy) | (16) COMMENT AGAINST (Baseline / Proposed Change) | (17) DOORS ID (if applicable) | (18) Requirement? Y/N | (19) Requirement Change Type | (20) DISPOSITION - Accept, Accept with Comment, Reject, or Defer | (21) DISPOSITION RATIONAL | (22) FINAL CHANGED TEXT (if not identical to suggested text or no suggestion offered) | (23) COMMENTER CONCURRENCE (Concur or Non Concur) | (24) NON CONCURRENCE RATIONAL (if applicable) | (25) CONCURRENCE METHOD (email, phone, mtg) | (26) DATE CONCURRENCE RECEIVED (mm/dd/yy) | (27) FINAL COMMENT STATUS (Open/Closed) | (28) NOTES
1 | 2 SOPS | DOAN | Steven T. Hutsell | N/A | N/A | S - Substantive | As indicated during the teleconference, we respectfully NON-concur with the [Reason For Change (Driver)]. If the intent is to try “to align ICD-GPS-240 with [text from an external document, whether the SPSPS, PPSPS, or otherwise]”, I’d recommend simply stating such instead of “Fix 2SOPS violations…..”, which comes across besmirching an Operations Squadron for otherwise innocently following orders from HHQ that were otherwise legally in compliance with the document applicable to the interface in question (ICD-GPS-240). | Fix 2SOPS violations of the SPS PS for NANU issuance. | Clarify SPS PS derived requirements for NANU issuance. | Does not place blame where none exists, provides clarification for reason for change. | Pre-WG | 2017-04-21 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | Final changed text (Reason For Change) to: "Clarify SPSPS derived requirements for NANU issuance." | Accept
2 | 2 SOPS | DOAN | Steven T. Hutsell | N/A | N/A | S - Substantive | We respectfully don’t see the need for the proposed change on the second page of the attached document (“The status and problem reporting…..”). Rationale: ICD-GPS-240 defines thresholds pertaining to interaction between the GPS CS and GUSS, the GPS CS and NAVCEN, and the GPS CS and military users. The injection of SPSPS and/or PPSPS education is not of immediate concern to the factions executing the interface. Additionally, the “…..are applicable requirements for DoD…..”, while of good intent I trust, may also unfortunately be asking for some legal consternation, given how the [Capital R] Requirements communities, who operate from their own sets of documents, might see this statement as blurring lanes of responsibility. ICD-GPS-240 already has enough drama of its own without having to contend with external document applicability wrangling. |  |  |  | Pre-WG | 2017-04-21 | Proposed Change |  | N |  | Accept | The rest of the PIRN wording will remain as "Is" due to the consensus and comments from other stakeholders. |  | NON-Concur. | Disposition partially rejects the comment. Disposition Rational vaguely cites "consensus and comments from other stakeholders", but offers no specifics, let alone technical rationale. Comment adjudications should be founded on technical rationale, not intimations of popularity. |  |  |  | Per TIM, held on 27Jul17, the suggested additional wording for ICD240-120 & ICD870-139 will be moved to the rationale section in DOORS for the document. With respect to ICD240-122 & ICD870-141, the wording in Table 10-IV, under the Threshold column, Schedule row, "per the performance standards", will be moved to the rationale section in DOORS (Technical Baseline Manager).
3 | Aerospace | GPE(Aero) | Karl l. Kovach | N/A | N/A | A - Administrative | The third page of PIRN-870B-002 more closely matches the recollection of Steven T. Hutsell regarding the wording proposed by Stephan M. Hillman in the prior teleconference. | <<no change>> | <<no change>> | <<no change>> | Pre-WG | 2017-04-21 | Proposed Change |  | N |  | Accept | None required
4 | Aerospace | GPE(Aero) | Karl l. Kovach | N/A | N/A | A - Administrative | On the coversheet for PIRN-870B-002, in the box labeled as "Reason for Change (Driver):", the words which currently read as "Fix 2SOPS violations of the SPS PS for NANU issuance" may appear to besmirch an Operations Squadron for otherwise innocently following orders from HHQ that were otherwise legally in compliance with the document otherwise applicable to the interface in question (ICD-GPS-240). | "Fix 2SOPS violations of the SPS PS for NANU issuance." | "Clarify PPS PS and SPS PS -derived requirements for NANU issuance." | Correctly put the blame for all those 'short notice' NANU violations earlier this year on a non-clearly worded ICD rather than on 2 SOPS. | Pre-WG | 2017-04-21 | Proposed Change |  | N |  | Accept | Incorporated suggested comment in PIRN release.
5 | Aerospace | GPE(Aero) | Karl l. Kovach | 8 to 11 | 10.2 "Is" | A - Administrative | Although 2 SOPS may not need to understand why they do what they do, GPS users are entitled to know why 2 SOPS does what they do. GPS users have access to the PPS PS and SPS PS and therefore understand that the Office of the Secretary of Defense has committed the DoD (which includes 2 SOPS) to meeting the status and problem reporting standards in the PPS PS and SPS PS. Including the proposed new words at the end of paragraph 10.2 helps U.S. and allied military users, plus an entire world of civil users, appreciate the entire DoD's dedication to upholding the commitments made by the Office of the Secretary of Defense. | <<no change>> | <<no change>> | <<no change>> | Pre-WG | 2017-04-21 | Proposed Change |  | N |  | Accept | None required
6-N/A | USAF | GPSW/GPV | Capt Bryan P. McCarthy |  |  | A-Administrative | No Impact |  |  |  | Pre-WG | 2017-04-27 | Proposed Change |  | N
7-N/A | USCG |  | CWO Rebecca Ruch |  |  | A-Administrative | No Comment |  |  |  | Pre-WG | 2017-05-16 | Proposed Change |  | N
8-N/A | USAF-GPSW/GPE |  | Capt Jenny Ji |  |  | A-Administrative | No Comment |  |  |  | Pre-WG | 2017-05-22 | Proposed Change |  | N
9-N/A | USAF | GPSW/GPD | Todd M. Kawakami |  |  | A-Administrative | No Comment |  |  |  | Pre-WG | 2017-05-24 | Proposed Change |  | N
6 | FAA | GPSW/GPC | Ha Nguyen |  | Table 10-IV | S - Substantive | Clarify intent of proposed Note 1 to state that the threshold will not be met. | NOTE 1: ... may not meet the Scheduled outage Threshold. | NOTE 1: ... will not meet the Scheduled outage Threshold. | A threshold is a firm limit, and if broken, the condition is not met. The word "may" leaves one in doubt as to whether Is the threshold is met or not, and should be replaced with "will". | Pre-WG | 2017-05-25 | Proposed Change |  | N |  | Accept | Will incorporated as suggested.
7 | FAA | GPSW/GPC | Ha Nguyen |  | Table 10-IV | S - Substantive | Clarify intent of proposed Note 1 to state that the threshold will not be met. | NOTE 1: ... may not meet the Scheduled outage Threshold. | NOTE 1: ... will not meet the Scheduled outage Threshold. | A threshold is a firm limit, and if broken, the condition is not met. The word "may" leaves one in doubt as to whether Is the threshold is met or not, and should be replaced with "will". | Pre-WG | 2017-05-25 | Proposed Change |  | N |  | Accept | Will incorporated as suggested.
8 (GPGX-01) | MITRE | GPSW/GPCG | David Hoki |  | ICD870-141 | S - Substantive | Language for scheduled "nominal notification times" is "NLT 48 hrs. & NET 96 hrs. prior to outage start". NLT (No later than) and NET (No earlier than) are confusing as a nominal time. The entry should be changed to "96 hours" which is what the 2008 SPS PS states multiple times. A note about the Loss of continuity metric for NANUs issued with less than 48 hours of interruption should be added as a note, but 48 hours is not the nominal time the SPS says OCS should post scheduled NANUs for. Additionally, the next update of the SPS PS should remove the statement "at least 96 hours in advance". It is 96 hours nominally, not at least 96 hours. OCS may give more than 96 hours notice but the nominal commitment is 96 hours. If that is not the intent of the SPS, then the SPS needs to be reworded to state consistent intent. |  |  |  | Pre-WG | 2017-05-30 | Proposed Change | ICD870-141 | N |  | Reject | Latest PIRN release no longer contains this language concerning NET, NLT, and Loss of Continuity with respect to Scheduled, Nominal Notification Times. Only the "Threshold" contains NLT. | Scheduled, Nominal Notification Times: "Nominally 96 hours prior to outage start." Scheduled, Threshold: "NLT 48 hrs. prior to outage start per the performance standards (see note #1)." | [5 empty] | Per Non-public Gov't ICWG (15Aug17), the comment was against an outdated/obsolete PIRN that was not formally published and does not contain the language the commenter is describing; therefore, this comment is rejected.
9 (GPGX-02) | MITRE | GPSW/GPCG | David Hoki |  | ICD870-141 | S - Substantive | WAS/IS language for unscheduled objective [notification time] is "15 minutes after outage start". This conflicts with higher precedence document SS-CS-800 CS3194 which says "...generate digital NANUs and make them available within 2 minutes from the time the status changed...". The ICD objective time should be as tight or tighter than the CS800 objective time. Recommend changing ICD870-141 IS language for unscheduled objective [notification time] to " within 2 minutes from the time the status changed until upload connection to USNO initiated" to be consistent with CS800. also recommend unscheduled nominal language to be "within 60 minutes from the time the status changed until upload connection to USNO initiated" |  |  |  | Pre-WG | 2017-05-30 | Proposed Change | ICD870-141 | N |  | Reject | CS3194 is an Effectivity 30 requirement not an Effectivity 10 requirement, and it does not fully encompass the full timeline called for by the table. Suggest this be revisited at that time. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment is against a non-validated requirement and requirements for Effectivity 30 have not been ascertained at present. Also, nothing is fixed until a new CDD is written. Comment is rejected.
14-N/A | LM GPS III COps |  | Jeffrey Crum |  | ICD240 | A - Administrative | No Comment |  |  |  | Pre-WG | 2017-05-31
10 | MITRE | SMC/GPE | Daniel O'Laughlin | 10.2, ICD870-139 |  | S - Substantive | In the NANU Notification Table (in both, PIRN-870B-002) the proposed change changes the heading of one column of the table from "Objective" to "Threshold". However, the text that reference the table still refers to it as an "Objective". (i.e., they state: Nominal and objective NANU notification times for the four NANU groups are summarized in Table 10-IV.) | NANU messages announcing scheduled events are normally distributed to the user community prior to the event. NANU messages announcing unscheduled events are normally distributed to the user community as soon as practical after the event. However, mission critical problems have priority over user notification and therefore may delay normal NANU distribution. NANU notification times typically vary by NANU group. Nominal and objective NANU notification times for the four NANU groups are summarized in Table 10-IV. The status and problem reporting standards given in the current editions of the GPS Precise Positioning Service Performance Standard (PPSPS) and GPS Standard Positioning Service Performance Standard (SPSPS) are applicable requirements for DoD. | NANU messages announcing scheduled events are normally distributed to the user community prior to the event. NANU messages announcing unscheduled events are normally distributed to the user community as soon as practical after the event. However, mission critical problems have priority over user notification and therefore may delay normal NANU distribution. NANU notification times typically vary by NANU group. Nominal and Threshold NANU notification times for the four NANU groups are summarized in Table 10-IV. The status and problem reporting standards given in the current editions of the GPS Precise Positioning Service Performance Standard (PPSPS) and GPS Standard Positioning Service Performance Standard (SPSPS) are applicable requirements for DoD. | Clarification | Pre-WG | 2017-05-31 | Baselined Doc | ICD870-139 | N |  | Accept | PIRN will be updated with proposed wording and spacing. |  | Concur |  | email | 2017-06-05 | Closed
11 | MITRE | SMC/GPE | Daniel O'Laughlin | 10.2, ICD240-120 |  | S - Substantive | In the NANU Notification Table (in PIRN-240A-003) the proposed change changes the heading of one column of the table from "Objective" to "Threshold". However, the text that reference the table still refers to it as an "Objective". (i.e., they state: Nominal and objective NANU notification times for the four NANU groups are summarized in Table 10-IV.) Also remove the space between (PPS PS) and (SPS PS) to be consistent with ICD870-139. | NANU messages announcing scheduled events are normally distributed to the user community prior to the event. NANU messages announcing unscheduled events are normally distributed to the user community as soon as practical after the event. However, mission critical problems have priority over user notification and therefore may delay normal NANU distribution. NANU notification times typically vary by NANU group. Nominal and objective NANU notification times for the four NANU groups are summarized in Table 10-IV. The status and problem reporting standards given in the current editions of the GPS Precise Positioning Service Performance Standard (PPS PS) and GPS Standard Positioning Service Performance Standard (SPS PS) are applicable requirements for DoD. | NANU messages announcing scheduled events are normally distributed to the user community prior to the event. NANU messages announcing unscheduled events are normally distributed to the user community as soon as practical after the event. However, mission critical problems have priority over user notification and therefore may delay normal NANU distribution. NANU notification times typically vary by NANU group. Nominal and Threshold NANU notification times for the four NANU groups are summarized in Table 10-IV. The status and problem reporting standards given in the current editions of the GPS Precise Positioning Service Performance Standard (PPSPS) and GPS Standard Positioning Service Performance Standard (SPSPS) are applicable requirements for DoD. | Clarification | Pre-WG | 2017-05-31 | Baselined Doc | ICD240-120 | N |  | Accept | PIRN will be updated with proposed wording and spacing. |  | Concur |  | email | 2017-06-05 | Closed
17-N/A | AFSPC | AFSPC/A5P | John Yarger |  |  | A - Administrative | No Comment |  |  |  |  | 2017-06-01
12 | Raytheon |  | Alex Snyder |  | ICD870-141 | A - Administrative | The use of threshold instead of objective is a bit confusing. The use of objective in requirements definition tends to be used as a "hard requirement" (critical performance) as supposed to 'good enough' effort -threshold. Suggest switching back to objective | Objective |  | clarification | Pre-WG | 2017-06-01 | Proposed Change | ICD870-141 | N |  | Reject | Consensus appears to support the use of "Threshold" vice "Objective". | [6 empty] | Decision to switch from "Objective" to "Threshold" was made at a TIM, 11Apr17, of all Directorate/Stakeholders.
19-N/A | Sandia National Laboratories |  | Jose. S.Salazar |  |  | A - Administrative | No Comment |  |  |  | Pre-WG | 2017-05-31 | Proposed Change |  | N
20-N/A | USAF | GPSW/GPV |  |  |  | A - Administrative | No Impact |  |  |  | Pre-WG | 2017-06-02 | Proposed Change |  | N
21-N/A | USAF |  | Rodney A. Houser |  |  | A - Administrative | No Comment |  |  |  | Pre-WG | 2017-06-02 | Proposed Change |  | N
22-N/A | USAF |  | Troy A. Tschirhart |  |  | A - Administrative | No Impact |  |  |  | Pre-WG | 2017-06-06 |  |  | N
23-N/A | USAF |  | Bruce Klein |  |  | A - Administrative | No Comment |  |  |  | Pre-WG | 2017-07-10 |  |  | N
24-N/A | Booz-Allen-Hamilton |  | Kris Fromm |  |  | A - Administrative | No Comment |  |  |  | Pre-WG | 2017-07-10 |  |  | N
25-N/A | USAF | GPSW/GPN | Ramon A Hilario |  |  | A - Administrative | No Comment |  |  |  | Pre-WG |  |  |  | N
13 | Gov |  | Lt Jared Pilcher | 10.2, ICD240-122 | Redlines to Table 10-IV | S - Substantive | Changing the Objective column to Threshold creates an issue with the Unscheduled row. "15 minutes after outage start" is an Objective metric but with the proposed changes would be listed under the Threshold column. |  | Move "NLT 48 hrs prior to outage start per the performance standards (see note #1)" under "Nominal Notification Times" |  | Pre-WG | 2017-08-04 | Proposed Change |  | N |  | Accept | Part of the wording will be moved to the rationale section in DOORS per agreement with 2 SOPS. The rest will remain as guidance. | NLT 48 hrs prior to outage start (see note #1) | [5 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was addressed in comments received during meeting (see comments 15-20). Comment was accepted.
14 |  |  | Lt Jared Pilcher | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | Changing the Objective column to Threshold creates an issue with the Unscheduled row. "15 minutes after outage start" is an Objective metric but with the proposed changes would be listed under the Threshold column. |  | Move "NLT 48 hrs prior to outage start per the performance standards (see note #1)" under "Nominal Notification Times" |  | Pre-WG | 2017-08-04 | Proposed Change |  | N |  | Accept | Part of the wording will be moved to the rationale section in DOORS per agreement with 2 SOPS. The rest will remain as guidance. | NLT 48 hrs prior to outage start (see note #1) | [5 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was addressed in comments received during meeting (see comments 15-20). Comment was accepted.
15 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD240-122 | Redlines to Table 10-IV | S - Substantive | Intuitively, why would a “Threshold” value be tighter (less than) a “Nominal” value. Rationale for the question: Intuitively, if (less than 1 hour but greater than 15 minutes) is in excess of “Threshold”, how can it be considered “Nominal”? | Nominal Notification Times (column): Less than 1 hr after outage start Threshold (column): 15 minutes after outage start | Nominal Notification Times (column): 15 minutes after outage start Threshold (column): Less than 1 hr after outage start | Remove confusion inherent in the outage notification times and place them in the proper columns, that is, swap them. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.
16 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD240-122 | Redlines to Table 10-IV | S - Substantive | Nominal is redundant under the "Nominal Notification Times" column, "Scheduled" row. Suggest removing it. | Nominally 96 hours prior to outage start. | 96 hours prior to outage start | Remove redundancy of wording. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.
17 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD240-122 | Redlines to Table 10-IV | S - Substantive | "No Nominal" is inaccurate under the "Nominal Notification Times" column, "General" and "Other" row. Suggest putting "None" instead. | No Nominal - Timing determined on a case-by-case basis. | None - Timing determined on a case-by-case basis. | Wording is more definitive and removes any ambiguity. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.
| 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | Intuitively, why would a “Threshold” value be tighter (less than) a “Nominal” value. Rationale for the question: Intuitively, if (less than 1 hour but greater than 15 minutes) is in excess of “Threshold”, how can it be considered “Nominal”?
| 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | Nominal is redundant under the "Nominal Notification Times" column, "Scheduled" row. Suggest removing it.
| 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | "No Nominal" is inaccurate under the "Nominal Notification Times" column, "General" and "Other" row. Suggest putting "None" instead.
18 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | Intuitively, why would a “Threshold” value be tighter (less than) a “Nominal” value. Rationale for the question: Intuitively, if (less than 1 hour but greater than 15 minutes) is in excess of “Threshold”, how can it be considered “Nominal”? | Nominal Notification Times (column): Less than 1 hr after outage start Threshold (column): 15 minutes after outage start | Nominal Notification Times (column): 15 minutes after outage start Threshold (column): Less than 1 hr after outage start | Remove confusion inherent in the outage notification times and place them in the proper columns, that is, swap them. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.
19 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | Nominal is redundant under the "Nominal Notification Times" column, "Scheduled" row. Suggest removing it. | Nominally 96 hours prior to outage start. | 96 hours prior to outage start | Remove redundancy of wording. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.
20 | 2 SOPS | DOAN | Steven T. Hutsell | 10.2, ICD870-141 | Redlines to Table 10-IV | S - Substantive | "No Nominal" is inaccurate under the "Nominal Notification Times" column, "General" and "Other" row. Suggest putting "None" instead. | No Nominal - Timing determined on a case-by-case basis. | None - Timing determined on a case-by-case basis. | Wording is more definitive and removes any ambiguity. | WG | 2017-08-14 | Proposed Change |  | N |  | Accept | Reason for Change has been re-worded in the PIRN. | [6 empty] | Per Non-public Gov't ICWG (15Aug17), this comment was validated as necessary, and changes were made in real-time.

## SETUP-Instructions
INSTRUCTIONS: PRE-REVIEW SETUP:
Following are the instructions for preparing the form GPS CDM 072308-03 JUN 10_ CRM_Template
1 | Save this template as a workbook. | Ensure "Save as type" = "Excel workbook (*.xlsx)
Using the file name format: CRM_<document number>.xlsx
Example: CRM_IDC-GPS-812.xlsx
2 | On the tab "CRM", enter: | <Enter ICC name>
<phone number>
<Enter Baseline Document ID>
<Enter the Proposed revision number>
<Enter Document Title>
<Enter review cycle date>
<Enter Technical Lead name, phone number>
3 | Delete this SETUP instruction sheet
4 | Save the workbook: | Ensure "Save as type" = "Excel workbook (*.xlsx)
Using the file name format: CRM_<document number>.xlsx
Example: CRM_IDC-GPS-812.xlsx
5 | Distribute the CRM workbook to reviewers
INSTRUCTIONS: POST-DISPOSITION:
Following are the instructions for preparing CRM metrics (v20091028):
1 | Insert metrics template | Right-click tab. Select "Insert…"
Select the template: "CRM_Metrics_template.yyyymmdd.xltm"
2 | On the tab "CRM Metrics - By Phase": | Click the "Refresh" button
3 | On the tab "CRM Metrics - By Entity": | Click the "Refresh" button
4 | Print the metrics

## INSTRUCTIONS
GENERAL:
Following are the instructions for form GPS CDM 072308-03 JUN 10_ CRM_Template
INSTRUCTIONS:
During the review process, comments, questions, concerns regarding the document under review is to be documented and communicated using the CRM. The Tech Lead or ICC will copy the CRM Template file to the CCPD Smartbook and fill out the CRM header information. The CRM, sheet 1 of this workbook, is initiated by the Commenter and provided to the Project Officer as directed in the timeline associated with the assigned task. Following are instructions for completing the CRM form: Insert rows in the "White" section only of the CRM sheet for additional needed comments, this preserves printing and metrics. Insert a row by positioning the cursor on row below where you want a new row to be entered above it, then click Home>Insert>Insert Sheet Row. Begin new paragraph by clicking Alt-Enter at the point that you want a new paragraph started in the text.
Technical Leads and ICC (Interface Control Contractor) completes the HEADER INFORMATION at top of form:
| ICC: | Replace text with the ICC (Interface Control Contractor) name and phone number.
Baslined Document (CCB Version): |  | Replace text with the Baselined Document number
| Proposed Change: | Replace text with the Proposed Change being reviewed
| Title: | Replace text with the Title of the Proposed Change Document
| Date: | Replace text with the Date the Document as last approved
| Tech Lead Name: | Replace text with the Technical Lead name and phone number.
Commenter completes:
1 | Comment No. | Number sequentially. This will be used to identify specific comments.
2 | Entity | Pick the Entity you represent, i.e., Gov, Aero, SE&I, etc.
3 | Office Symbol | Pick the office symbol you are assigned to, i.e., ENR, GPC, etc.
4 | Comment Originator Name | Enter your name, Rank (as required) First, Middle Initial, Last Name
5 | Phone # | Enter the phone number where you may be reached.
6 | Email | Enter the e-mail where you may be reached.
7 | Document Line # | Enter the document line number if paragraph number in not applicable.
8 | Paragraph # | Enter the paragraph number your comment relates to. i.e., 3., 3.0, 3.1.1, 3.1.1.1, etc.
9 | Comment Type (C/S/A) | Pick the "Type" code that best fits the importance of the proposed change. Use the Comment Type Code Table below. (Critical/Substantive/Administrative)
10 | Comment | Enter comment or question about text.
11 | Original Text (FROM) | Enter the original text from the document being reviewed (Baseline Doc, PIRN, or IRN)
12 | Suggested Change (TO) | Enter the change that you, as a commenter, recommend.
13 | Rationale for Change | Enter your rationale for the change.
Technical Leads and ICC completes:
14 | Doc Phase | Pick the phase in which the comment is made. (PRE-WG, WG, WTR, POST-WTR) PRE-WG = Deferred comments from a previous change iteration WG = Comments as a result of any Working Group WTR = Comments as a result of the Wing Technical Review POST-WTR = Comments made after the ERB or CCB
15 | Date of Comment | Enter the date (mm/dd/yy) the comment is made or new text suggested.
16 | Comment Against (Baseline/ Proposed Change) | Choose whether you are commenting against the Baseline Document or Proposing a Change.
17 | DOORS ID (if applicable) | Enter the DOORS Id from the DOORS Data Base.
18 | Requirement? | Pick whether the DOORS Id is a Contract Requirement. Y = Yes or N = No.
19 | Requirement Change Type | Pick the type of change to the requirement: Addition, Change, Clarification, or Deletion.
20 | Disposition | Pick your disposition of each comment provided by the Commenter. Use the Comment Resolution Code Table below to choose whether you Accept, Accept with Comment, Reject, or Deferred the comment.
21 | Disposition Rational | Enter the rational for the disposition status
22 | Final Changed Text | Enter the final text agreed to if there is a re-evaluation. If no re-evaluation, the text suggested in column 16 will be final.
Commenter completes:
23 | Commenter Concurrence (Concur or Non Concur) | Pick the concurrence of the final text and/or disposition.
24 | Non Concurrence Rationale | Enter the Rationale, if Commenter does not agree with the ICC's disposition
Technical Leads and ICC completes:
25 | Concurrence Method (email, phone, mtg) | Pick the method Concurrence received
26 | Date Concurrence Received | Enter the date Concurrence received
27 | Final Comment Status | Enter the Final Comment Status (Open/Closed)
28 | Notes | Notes
COMMENTER:
The commenter assigns an importance code to each comment provided on the CRM. Below is the table to be used in determining comment importance.
COMMENT TYPE CODE TABLE
Code | Importance | Definition
C | Critical | Comments of a very serious nature that will preclude final approval and publication of the document. You are willing to elevate the comment or issue to senior organizational leadership (e.g., general officer) and recommend they non-concur. These are the “show-stoppers.” Convincing rationale for critical comments must be provided. The individual making the comment and the document writer will reconcile the comment.
S | Substantive | Comments of a less serious nature that have noticeable impact on the document’s quality or content. The document appears to be incorrect, misleading, confusing, or inconsistent with other sections.
A | Administrative | Comments that address minor items such as typographical, format, and/or grammatical errors.
Technical Leads and ICC:
The Technical Leads or ICC (Interface Control Contractor) upon review of each comment, assigns a recommendation code from one of the following. As necessary, the ICC also provides reasoning regarding the assigned disposition. Below is the table to be used in determining comment resolution.
COMMENT RESOLUTION CODE TABLE
Code | Recommendation | Definition
A | Accept | Accept comment as written. No change.
A/C | Accept with Comment | Accept comment with changes, providing detailed explanation. The individual making the comment and the ICC will reconcile the comment.
D | Deferred | Comments are administrative and will be included in the next change, or the comments are not within the scope of the proposed request for CCB disposition.
R | Reject | ICC will provide a rationale for rejection. For example, rationale will include “comment not technically sound, not cost effective, or cosmetic in nature”.